## Slide 1: Transition Status Report
IBM INDIA
21Mar2017
Prepared for Heineken International B.V.

## Slide 2: HEINEKEN AMS Support Transition Timelines
Transition approach by IBM
Oct, 2016
Prepared by :albert.veldhoven@nl.ibm.com

## Slide 3: Transition Planning Approach
GP can start ideally after UAT has been finalized
GP needs to be finalized (1 week) before Toll gate meeting for the release
IBM will move to AP the moment the software has been moved to Production.
Only after Business Go live the transition will proceed as of that time only the software will be used and at least 2 weeks of AP
AP
PP
GP
Business
Go live
Technical
Go live
Release
UAT
Go / No
Go call
to AP
Steady
State
Toll gate
Release
Go / No
Go call
to SS
Go / No
Go call
to PP

## Slide 4
 | In Flight | Vendor Managed | New App
Total Projects | 205 | 6 | 31
Formally Closed | 176 | 5 | 25
Current WIP Projects | 26 | 1 | 5
Intake to be done + Hold + No Pursuit | 3 | 0 | 1
Overall Transition Status
Jan-16 | Feb-16 | Mar-16 | Apr-16 | May-16 | June-16 | Jul-16 | Aug-16 | Sep-16 | Oct-16 | Nov-16 | Dec-16
6 | 3 | 12 | 7 | 15 | 2 | 10 | 11 | 4 | 10 | 2 | 9
Projects Closed during the month
Jan-16 | Feb-16 | Mar-16 | Apr-16 | May-16 | June-16 | Jul-16 | Aug-16 | Sep-16 | Oct-16 | Nov-16 | Dec-16
 |  | 2 | 1 | 5 | 1 | 2 | 1 |  | 7 | 2 | 1
In Flight
New Apps

## Slide 5: Transition Master Plan

## Slide 6: Content
Inflight Projects

## Slide 7: Inflight Project(s) – Harish / Benjamin
HeiXS – Interfaces Logistic Process
  PP Phase Go/NoGo – To be planned.
C&TP Flight Enhancements (Mar-17)
  AP Phase – In Progress as planned from 20Mar.
C&TP Flight Enhancements (Apr-17) - 1 CR (CHG0153146). Go Live on 23Apr.
  AP Phase from 24Apr. KT Session completed.

## Slide 8: Inflight Project(s) – Harish / Edger de Mots
FSCM - Enhancement - CHG0154357 (Feb release)
  SS Phase : In Progress. Hand over to AMS Support
FSCM - Enhancement (Apr release)
  GP Phase : From 27Mar – Planned. KT session scheduled
  Apr release :
  CHG0157790 : Part 3 - FSCM : DCD Search Result Fields
  CHG0157789 : Part 3 – ECC : DCD Search Result Fields
  CHG0154356 : Part 2 – ECC : Customer Statement
  CHG0161765 : Part 4 - FSCM : Dispute ; add attachment & Improve Mail

## Slide 9: Inflight Project(s) – Harish / ??
Sourcing – 3 CR’s (CHG0160919, CHG0160918, CHG0160915 - Apr Release)
  ASP Phase : In Progress
  GP Phase : Agreed. Planned from 27Mar for 3 CR’s planned for Apr.
  CHG0160919 : Project Field Enhancements v2
  CHG0160918 : 05. BRD CSP Document Type creation
  CHG0160915 : 01.BRD - Approval - Phase - Clicks reduction v2

## Slide 10: Overall View of Inflight Projects – 21-Mar

## Slide 11: New Projects / Change Requests Added [Details to be obtained]

## Slide 12: Inflight Project(s) view under Sharon

## Slide 13
Heilite 2.0 - Plan on Page for All the new Opcos

## Slide 14: Heilite 2.0 (Brarudi) GoLive Delayed, plan updated accordingly.
Heilite 2.0 (Ivory Coast) – To be Replanned - Update Awaited from Ton,
Heilite 2.0 ( Ethiopia) – Updated Plan to be obtained from Ton

## Slide 15: Inflight Project(s) view under Benjamin

## Slide 16: Project(s) view under Edger de Mots

## Slide 17: Update on External Access Sharepoint

## Slide 18: Summary of the Inflight projects with Reasons for Delay ( Under review by Service Coordinators)